## Stakeholder Register
Stakeholder ID | Stakeholder Name | Department | Role | Interest Level | Influence Level | Priority | Expectations
ST-001 | CEO | Executive | Project Sponsor | High | High | Critical | Reduce churn and revenue loss
ST-002 | Marketing Manager | Marketing | Business User | High | High | Critical | Identify high-risk customers
ST-003 | Customer Support Manager | Operations | Business User | High | Medium | High | Improve customer satisfaction
ST-004 | Sales Manager | Sales | Business User | Medium | Medium | Medium | Increase customer retention
ST-005 | Business Analyst | Business Analysis | Requirement Owner | High | High | Critical | Deliver business solution
ST-006 | Data Analyst | Analytics | Data Owner | High | Medium | High | Accurate insights and reporting
ST-007 | Customers | External | End User | High | Low | Medium | Better service experience

## Power-Interest Matrix
Stakeholder | Power | Interest | Engagement Strategy
CEO | High | High | Manage Closely
Marketing Manager | High | High | Manage Closely
Business Analyst | High | High | Manage Closely
Customer Support Manager | Medium | High | Keep Informed
Data Analyst | Medium | High | Keep Informed
Sales Manager | Medium | Medium | Monitor
Customers | Low | High | Keep Informed

## Communication Plan
Stakeholder | Communication Type | Frequency | Method | Owner
CEO | Project Status Update | Weekly | Email/Meeting | BA
Marketing Manager | Requirement Discussion | Weekly | Meeting | BA
Customer Support Manager | Feedback Session | Bi-weekly | Teams Meeting | BA
Sales Manager | Progress Review | Monthly | Email | BA
Data Analyst | Data Validation | Weekly | Teams Meeting | BA

## RACI Matrix
Activity | CEO | Marketing | Customer Support | Sales | BA | Data Analyst
Requirement Gathering | I | C | C | C | A/R | I
Data Collection | I | I | I | I | C | A/R
Data Analysis | I | C | I | I | C | A/R
Dashboard Development | I | C | I | I | A | R
UAT | C | A/R | A/R | C | R | C
Final Approval | A | C | C | C | R | I

## Stakeholder Requirements
Stakeholder | Requirement | Priority
CEO | View churn trends and revenue loss | High
Marketing Manager | Identify high-risk customers | High
Customer Support Manager | Analyze service issues causing churn | High
Sales Manager | Identify retention opportunities | Medium
Data Analyst | Access clean customer data | Medium

## Risk Assessment
Stakeholder | Risk | Impact | Mitigation
CEO | Delayed approval | High | Weekly updates
Marketing Manager | Changing requirements | Medium | Requirement sign-off
Data Analyst | Data quality issues | High | Data validation checks